## Order Module
Project Name: | Printing Kiosk System | Test Designed by: | Yoon Wei Kai
Module Name: | Order Module | Test Designed date: | 2023-04-12
Release Version: | V 1.3 | Test Executed by: | E Zhong Lin
|  | Test Execution date: | 2023-04-16
Pre-condition | -
Dependencies: | -
Test Priority | 3 (High)
Test File Name | Test Case# | Test Title | Test Summary | Pre-condition | Test Steps | Test Data | Expected Result | Post-condition | Actual Result | Status | Notes
OrderUnitTests.java | 1.1.1 | Verify Order Type | Enter the valid order type | - | 1. Set Order Type 2. Get Order Type | Type = "D" | "D" | - | "D" | Pass | -
| 1.1.2 |  | Enter the valid order type in lowercase | - | 1. Set Order Type 2. Get Order Type | Type = "d" | "D" | - | "D" | Pass | -
| 1.1.3 |  | Enter the invalid order type(null) | - | 1. Set Order Type 2. Get Order Type | Type = null | throw IllegalArgumentException | "Type cannot be null\n" | throw IllegalArgumentException | Pass | -
| 1.1.4 |  | Enter the invalid order type | - | 1. Set Order Type 2. Get Order Type | Type = "do" | throw IllegalArgumentException | "Invalid type.Please enter again.\n" | throw IllegalArgumentException | Pass | -
| 1.1.5 |  | Enter the blank order type | - | 1. Set Order Type 2. Get Order Type | Type = "" | throw IllegalArgumentException | "Invalid type.Please enter again.\n" | throw IllegalArgumentException | Pass | -
| 1.2.1 | Verify Order Option | Enter the valid order option | - | 1. Set Order Option 2. Get Order Option | Option = 1 | 1 | - | 1 | Pass | -
| 1.2.2 |  | Enter the invalid order option (Invalid Low) | - | 1. Set Order Option 2. Get Order Option | Option = 0 | throw IllegalArgumentException | "Invalid option.Please enter again.\n" | throw IllegalArgumentException | Pass | -
| 1.2.3 |  | Enter the invalid order option (Invalid High) | - | 1. Set Order Option 2. Get Order Option | Option = 3 | throw IllegalArgumentException | "Invalid option.Please enter again.\n" | throw IllegalArgumentException | Pass | -
| 1.3.1 | Verify Order Quantity | Enter the valid order quantity | - | 1. Set Order Quantity 2. Get Order Quantity | Quantity = 1 | 1 | - | 1 | Pass | -
| 1.3.2 |  | Enter the invalid order quantity (Invalid Low) | - | 1. Set Order Quantity 2. Get Order Quantity | Quantity = 0 | throw IllegalArgumentException | "Invalid quantity.Please enter again.\n" | throw IllegalArgumentException | Pass | -
| 1.3.3 |  | Enter the invalid order quantity (Invalid High) | - | 1. Set Order Quantity 2. Get Order Quantity | Quantity = 51 | throw IllegalArgumentException | "Invalid quantity.Please enter again.\n" | throw IllegalArgumentException | Pass | -
| 1.4.1 | Verify Order Additional Option 1 | Enter the valid order info for additional option 1 | - | 1. Set Order Additional Option 1 2. Get Order Additional Option 1 | Additional Option 1 = "Y" | "Y" | - | "Y" | Pass | -
| 1.4.2 |  | Enter the valid order info for additional option 1 in lowercase | - | 1. Set Order Additional Option 1 2. Get Order Additional Option 1 | Additional Option 1 = "y" | "Y" | - | "Y" | Pass | -
| 1.4.3 |  | Enter the invalid order info for additional option 1(null) | - | 1. Set Order Additional Option 1 2. Get Order Additional Option 1 | Additional Option 1 = null | throw IllegalArgumentException | "Invalid choice.Please enter again.\n" | throw IllegalArgumentException | Pass | -
| 1.4.4. |  | Enter the invalid order info for additional option 1 | - | 1. Set Order Additional Option 1 2. Get Order Additional Option 1 | Additional Option 1 = "do" | throw IllegalArgumentException | "Invalid choice.Please enter again.\n" | throw IllegalArgumentException | Pass | -
| 1.4.5 |  | Enter the blank order info for additional option 1 | - | 1. Set Order Additional Option 1 2. Get Order Additional Option 1 | Additional Option 1 = "" | throw IllegalArgumentException | "Invalid choice.Please enter again.\n" | throw IllegalArgumentException | Pass | -
| 1.5.1 | Verify Order Additional Option 2 | Enter the valid order info for additional option 2 | - | 1. Set Order Additional Option 2 2. Get Order Additional Option 2 | Additional Option 2 = "Y" | "Y" | - | "Y" | Pass | -
| 1.5.2 |  | Enter the valid order info for additional option 2 in lowercase | - | 1. Set Order Additional Option 2 2. Get Order Additional Option 2 | Additional Option 2 = "y" | "Y" | - | "Y" | Pass | -
| 1.5.3 |  | Enter the invalid order info for additional option 2(null) | - | 1. Set Order Additional Option 2 2. Get Order Additional Option 2 | Additional Option 2 = null | throw IllegalArgumentException | "Invalid choice.Please enter again.\n" | throw IllegalArgumentException | Pass | -
| 1.5.4 |  | Enter the invalid order info for additional option 2(null) | - | 1. Set Order Additional Option 2 2. Get Order Additional Option 2 | Additional Option 2 = "do" | throw IllegalArgumentException | "Invalid choice.Please enter again.\n" | throw IllegalArgumentException | Pass | -
| 1.5.5 |  | Enter the blank order info for additional option 2 | - | 1. Set Order Additional Option 2 2. Get Order Additional Option 2 | Additional Option 2 = "" | throw IllegalArgumentException | "Invalid choice.Please enter again.\n" | throw IllegalArgumentException | Pass | -
AddCustomerOrderUnitTests.java | 2.1.1 | Verify Customer Order before adding it to List | Add the valid order | OrderList has been initialized | 1. Add Customer Order 2. Get Order List | Type = "D" Option = 1 Quantity = 1 Additional Option 1 = "N" Additional Option 2 = "N" | "D", 1, 2, "N", "N" | - | "D", 1, 2, "N", "N" | Pass | -
| 2.1.2 |  | Add invalid order (null value for order) | OrderList has been initialized | 1. Add Customer Order 2. Get Order List | Order = null | throw IllegalArgumentException | Order cannot be null | throw IllegalArgumentException | Pass | -
| 2.1.3 |  | Add invalid order(null value for type) | OrderList has been initialized | 1. Add Customer Order 2. Get Order List | Type = null Option = 1 Quantity = 1 Additional Option 1 = "N" Additional Option 2 = "N" | throw IllegalArgumentException | Order type is incorrect | throw IllegalArgumentException | Pass | -
| 2.1.4 |  | Add invalid order (invalid value for type) | OrderList has been initialized | 1. Add Customer Order 2. Get Order List | Type = "do" Option = 1 Quantity = 1 Additional Option 1 = "N" Additional Option 2 = "N" | throw IllegalArgumentException | Order type is incorrect | throw IllegalArgumentException | Pass | -
| 2.1.5 |  | Add invalid order (blank value for type) | OrderList has been initialized | 1. Add Customer Order 2. Get Order List | Type = "" Option = 1 Quantity = 1 Additional Option 1 = "N" Additional Option 2 = "N" | throw IllegalArgumentException | Order type is incorrect | throw IllegalArgumentException | Pass | -
| 2.1.6 |  | Add invalid order (invalid low value for option) | OrderList has been initialized | 1. Add Customer Order 2. Get Order List | Type = "D" Option = 0 Quantity = 1 Additional Option 1 = "N" Additional Option 2 = "N" | throw IllegalArgumentException | Order option is out of range | throw IllegalArgumentException | Pass | -
| 2.1.7 |  | Add invalid order (invalid high value for option) | OrderList has been initialized | 1. Add Customer Order 2. Get Order List | Type = "D" Option = 3 Quantity = 1 Additional Option 1 = "N" Additional Option 2 = "N" | throw IllegalArgumentException | Order option is out of range | throw IllegalArgumentException | Pass | -
| 2.1.8 |  | Add invalid order (invalid low value for quantity) | OrderList has been initialized | 1. Add Customer Order 2. Get Order List | Type = "D" Option = 1 Quantity = 0 Additional Option 1 = "N" Additional Option 2 = "N" | throw IllegalArgumentException | Order quantity is out of range | throw IllegalArgumentException | Pass | -
| 2.1.9 |  | Add invalid order (invalid high value for quantity) | OrderList has been initialized | 1. Add Customer Order 2. Get Order List | Type = "D" Option = 1 Quantity = 51 Additional Option 1 = "N" Additional Option 2 = "N" | throw IllegalArgumentException | Order quantity is out of range | throw IllegalArgumentException | Pass | -
| 2.1.10 |  | Add invalid order (null value for addOption1) | OrderList has been initialized | 1. Add Customer Order 2. Get Order List | Type = "D" Option = 1 Quantity = 1 Additional Option 1 = null Additional Option 2 = "N" | throw IllegalArgumentException | Order additional option 1 is incorrect | throw IllegalArgumentException | Pass | -
| 2.1.11 |  | Add invalid order (invalid value for addOption1) | OrderList has been initialized | 1. Add Customer Order 2. Get Order List | Type = "D" Option = 1 Quantity = 1 Additional Option 1 = "do" Additional Option 2 = "N" | throw IllegalArgumentException | Order additional option 1 is incorrect | throw IllegalArgumentException | Pass | -
| 2.1.12 |  | Add invalid order (blank value for addOption1) | OrderList has been initialized | 1. Add Customer Order 2. Get Order List | Type = "D" Option = 1 Quantity = 1 Additional Option 1 = "" Additional Option 2 = "N" | throw IllegalArgumentException | Order additional option 1 is incorrect | throw IllegalArgumentException | Pass | -
| 2.1.13 |  | Add invalid order (null value for addOption2) | OrderList has been initialized | 1. Add Customer Order 2. Get Order List | Type = "D" Option = 1 Quantity = 1 Additional Option 1 = "N" Additional Option 2 = null | throw IllegalArgumentException | Order additional option 2 is incorrect | throw IllegalArgumentException | Pass | -
| 2.1.14 |  | Add invalid order (invalid value for addOption2) | OrderList has been initialized | 1. Add Customer Order 2. Get Order List | Type = "D" Option = 1 Quantity = 1 Additional Option 1 = "N" Additional Option 2 = "do" | throw IllegalArgumentException | Order additional option 2 is incorrect | throw IllegalArgumentException | Pass | -
| 2.1.15 |  | Add invalid order (Order type is "D", but AddOption1 is "Y") | OrderList has been initialized | 1. Add Customer Order 2. Get Order List | Type = "D" Option = 1 Quantity = 1 Additional Option 1 = "Y" Additional Option 2 = "N" | throw IllegalArgumentException | Order with Document cannot have high quality paper effect and design effect | throw IllegalArgumentException | Pass | -
| 2.1.16 |  | Add invalid order (Order type is "D", but addOption2 is "Y") | OrderList has been initialized | 1. Add Customer Order 2. Get Order List | Type = "D" Option = 1 Quantity = 1 Additional Option 1 = "N" Additional Option 2 = "Y" | throw IllegalArgumentException | Order with Document cannot have high quality paper effect and design effect | throw IllegalArgumentException | Pass | -

## Charge Module
Project Name: | Printing Kiosk System | Test Designed by: | Yoon Wei Kai
Module Name: | Charge Module | Test Designed date: | 2023-04-13
Release Version: | V 1.3 | Test Executed by: | E Zhong Lin
|  | Test Execution date: | 2023-04-17
Pre-condition | -
Dependencies: | -
Test Priority | 3 (High)
Test File Name | Test Case# | Test Title | Test Summary | Pre-condition | Test Steps | Test Data | Expected Result | Post-condition | Actual Result | Status | Notes
CalculateEachDocChargeUnitTests.java | 1.1.1 | Verify the charge calculation of 1 Document Order | Calculate the charge of Black & White Document with quantity of 1 | 1. Order has been made and added to the order list. | 1. Calculate Document Charge | Type = "D" , Option = 1, Quantity = 1, Additional Option 1 = "N", Additional Option 2 = "N" | Charge = RM 0.5 | - | Charge = RM 0.5 | Pass | -
| 1.1.2 |  | Calculate the charge of Black & White Document with quantity of 4 | 1. Order has been made and added to the order list. | 1. Calculate Document Charge | Type = "D", Option = 1, Quantity = 4, Additional Option 1 = "N", Additional Option 2 = "N" | Charge = RM 2 | - | Charge = RM 2 | Pass | -
| 1.1.3 |  | Calculate the charge of Black & White Document with quantity of 5 | 1. Order has been made and added to the order list. | 1. Calculate Document Charge | Type = "D", Option = 1, Quantity = 5, Additional Option 1 = "N", Additional Option 2 = "N" | Charge = RM 2 | - | Charge = RM 2 | Pass | -
| 1.1.4 |  | Calculate the charge of Black & White Document with quantity of 10 | 1. Order has been made and added to the order list. | 1. Calculate Document Charge | Type = "D", Option = 1, Quantity = 10, Additional Option 1 = "N", Additional Option 2 = "N" | Charge = RM 4 | - | Charge = RM 4 | Pass | -
| 1.1.5 |  | Calculate the charge of Black & White Document with quantity of 11 | 1. Order has been made and added to the order list. | 1. Calculate Document Charge | Type = "D", Option = 1, Quantity = 11, Additional Option 1 = "N", Additional Option 2 = "N" | Charge = RM 3.3 | - | Charge = RM 3.3 | Pass | -
| 1.1.6 |  | Calculate the charge of Black & White Document with quantity of 20 | 1. Order has been made and added to the order list. | 1. Calculate Document Charge | Type = "D", Option = 1, Quantity = 20, Additional Option 1 = "N", Additional Option 2 = "N" | Charge = RM 6 | - | Charge = RM 6 | Pass | -
| 1.1.7 |  | Calculate the charge of Black & White Document with quantity of 21 | 1. Order has been made and added to the order list. | 1. Calculate Document Charge | Type = "D", Option = 1, Quantity = 21, Additional Option 1 = "N", Additional Option 2 = "N" | Charge = RM 4.2 | - | Charge = RM 4.2 | Pass | -
| 1.1.8 |  | Calculate the charge of Black & White Document with quantity of 50 | 1. Order has been made and added to the order list. | 1. Calculate Document Charge | Type = "D", Option = 1, Quantity = 50, Additional Option 1 = "N", Additional Option 2 = "N" | Charge = RM 10 | - | Charge = RM 10 | Pass | -
| 1.1.9 |  | Calculate the charge of Colour Document with quantity of 1 | 1. Order has been made and added to the order list. | 1. Calculate Document Charge | Type = "D", Option = 2, Quantity = 1, Additional Option 1 = "N", Additional Option 2 = "N" | Charge = RM 1 | - | Charge = RM 1 | Pass | -
| 1.1.10 |  | Calculate the charge of Colour Document with quantity of 4 | 1. Order has been made and added to the order list. | 1. Calculate Document Charge | Type = "D", Option = 2, Quantity = 4, Additional Option 1 = "N", Additional Option 2 = "N" | Charge = RM 4 | - | Charge = RM 4 | Pass | -
| 1.1.11 |  | Calculate the charge of Colour Document with quantity of 5 | 1. Order has been made and added to the order list. | 1. Calculate Document Charge | Type = "D", Option = 2, Quantity = 5, Additional Option 1 = "N", Additional Option 2 = "N" | Charge = RM 4.5 | - | Charge = RM 4.5 | Pass | -
| 1.1.12 |  | Calculate the charge of Colour Document with quantity of 10 | 1. Order has been made and added to the order list. | 1. Calculate Document Charge | Type = "D", Option = 2, Quantity = 10, Additional Option 1 = "N", Additional Option 2 = "N" | Charge = RM 9 | - | Charge = RM 9 | Pass | -
| 1.1.13 |  | Calculate the charge of Colour Document with quantity of 11 | 1. Order has been made and added to the order list. | 1. Calculate Document Charge | Type = "D", Option = 2, Quantity = 11, Additional Option 1 = "N", Additional Option 2 = "N" | Charge = RM 8.8 | - | Charge = RM 8.8 | Pass | -
| 1.1.14 |  | Calculate the charge of Colour Document with quantity of 20 | 1. Order has been made and added to the order list. | 1. Calculate Document Charge | Type = "D", Option = 2, Quantity = 20, Additional Option 1 = "N", Additional Option 2 = "N" | Charge = RM 16 | - | Charge = RM 16 | Pass | -
| 1.1.15 |  | Calculate the charge of Colour Document with quantity of 21 | 1. Order has been made and added to the order list. | 1. Calculate Document Charge | Type = "D", Option = 2, Quantity = 21, Additional Option 1 = "N", Additional Option 2 = "N" | Charge = RM 14.7 | - | Charge = RM 14.7 | Pass | -
| 1.1.16 |  | Calculate the charge of Colour Document with quantity of 50 | 1. Order has been made and added to the order list. | 1. Calculate Document Charge | Type = "D", Option = 2, Quantity = 50, Additional Option 1 = "N", Additional Option 2 = "N" | Charge = RM 35 | - | Charge = RM 35 | Pass | -
CalculateEachPhotoChargeUnitTests.java | 2.1.1 | Verify the charge calculation of 1 Photo Order | Calculate the charge of Normal (4R) photo with quantity of 1, without any additional effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 1, Quantity = 1, Additional Option 1 = "N" , Additional Option 2 = "N" | Charge = RM 1 | - | Charge = RM 1 | Pass | -
| 2.1.2 |  | Calculate the charge of Normal (4R) photo with quantity of 4, without any additional effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 1, Quantity = 4, Additional Option 1 = "N", Additional Option 2 = "N" | Charge = RM 4 | - | Charge = RM 4 | Pass | -
| 2.1.3 |  | Calculate the charge of Normal (4R) photo with quantity of 5, without any additional effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 1, Quantity = 5, Additional Option 1 = "N", Additional Option 2 = "N" | Charge = RM 4.5 | - | Charge = RM 4.5 | Pass | -
| 2.1.4 |  | Calculate the charge of Normal (4R) photo with quantity of 10, without any additional effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 1, Quantity = 10, Additional Option 1 = "N", Additional Option 2 = "N" | Charge = RM 9 | - | Charge = RM 9 | Pass | -
| 2.1.5 |  | Calculate the charge of Normal (4R) photo with quantity of 11, without any additional effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 1, Quantity = 11, Additional Option 1 = "N", Additional Option 2 = "N" | Charge = RM 8.25 | - | Charge = RM 8.25 | Pass | -
| 2.1.6 |  | Calculate the charge of Normal (4R) photo with quantity of 20, without any additional effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 1, Quantity = 20, Additional Option 1 = "N", Additional Option 2 = "N" | Charge = RM 15 | - | Charge = RM 15 | Pass | -
| 2.1.7 |  | Calculate the charge of Normal (4R) photo with quantity of 21, without any additional effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 1, Quantity = 21, Additional Option 1 = "N", Additional Option 2 = "N" | Charge = RM 10.5 | - | Charge = RM 10.5 | Pass | -
| 2.1.8 |  | Calculate the charge of Normal (4R) photo with quantity of 50, without any additional effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 1, Quantity = 50, Additional Option 1 = "N", Additional Option 2 = "N" | Charge = RM 25 | - | Charge = RM 25 | Pass | -
| 2.1.9 |  | Calculate the charge of Normal (4R) photo with quantity of 1, with high quality paper effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 1, Quantity = 1, Additional Option 1 = "Y", Additional Option 2 = "N" | Charge = RM 1.1 | - | Charge = RM 1.1 | Pass | -
| 2.1.10 |  | Calculate the charge of Normal (4R) photo with quantity of 4, with high quality paper effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 1, Quantity = 4, Additional Option 1 = "Y", Additional Option 2 = "N" | Charge = RM 4.4 | - | Charge = RM 4.4 | Pass | -
| 2.1.11 |  | Calculate the charge of Normal (4R) photo with quantity of 5, with high quality paper effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 1, Quantity = 5, Additional Option 1 = "Y", Additional Option 2 = "N" | Charge = RM 5 | - | Charge = RM 5 | Pass | -
| 2.1.12 |  | Calculate the charge of Normal (4R) photo with quantity of 10, with high quality paper effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 1, Quantity = 10, Additional Option 1 = "Y", Additional Option 2 = "N" | Charge = RM 10 | - | Charge = RM 10 | Pass | -
| 2.1.13 |  | Calculate the charge of Normal (4R) photo with quantity of 11, with high quality paper effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 1, Quantity = 11, Additional Option 1 = "Y", Additional Option 2 = "N" | Charge = RM 9.35 | - | Charge = RM 9.35 | Pass | -
| 2.1.14 |  | Calculate the charge of Normal (4R) photo with quantity of 20, with high quality paper effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 1, Quantity = 20, Additional Option 1 = "Y", Additional Option 2 = "N" | Charge = RM 17 | - | Charge = RM 17 | Pass | -
| 2.1.15 |  | Calculate the charge of Normal (4R) photo with quantity of 21, with high quality paper effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 1, Quantity = 21, Additional Option 1 = "Y", Additional Option 2 = "N" | Charge = RM 12.6 | - | Charge = RM 12.6 | Pass | -
| 2.1.16 |  | Calculate the charge of Normal (4R) photo with quantity of 50, with high quality paper effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 1, Quantity = 50, Additional Option 1 = "Y", Additional Option 2 = "N" | Charge = RM 30 | - | Charge = RM 30 | Pass | -
| 2.1.17 |  | Calculate the charge of Normal (4R) photo with quantity of 1, with design effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 1, Quantity = 1, Additional Option 1 = "N", Additional Option 2 = "Y" | Charge = RM 1.15 | - | Charge = RM 1.15 | Pass | -
| 2.1.18 |  | Calculate the charge of Normal (4R) photo with quantity of 4, with design effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 1, Quantity = 4, Additional Option 1 = "N", Additional Option 2 = "Y" | Charge = RM 4.6 | - | Charge = RM 4.6 | Pass | -
| 2.1.19 |  | Calculate the charge of Normal (4R) photo with quantity of 5, with design effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 1, Quantity = 5, Additional Option 1 = "N", Additional Option 2 = "Y" | Charge = RM 5.25 | - | Charge = RM 5.25 | Pass | -
| 2.1.20 |  | Calculate the charge of Normal (4R) photo with quantity of 10, with design effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 1, Quantity = 10, Additional Option 1 = "N", Additional Option 2 = "Y" | Charge = RM 10.5 | - | Charge = RM 10.5 | Pass | -
| 2.1.21 |  | Calculate the charge of Normal (4R) photo with quantity of 11, with design effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 1, Quantity = 11, Additional Option 1 = "N", Additional Option 2 = "Y" | Charge = RM 9.9 | - | Charge = RM 9.9 | Pass | -
| 2.1.22 |  | Calculate the charge of Normal (4R) photo with quantity of 20, with design effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 1, Quantity = 20, Additional Option 1 = "N", Additional Option 2 = "Y" | Charge = RM 18 | - | Charge = RM 18 | Pass | -
| 2.1.23 |  | Calculate the charge of Normal (4R) photo with quantity of 21, with design effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 1, Quantity = 21, Additional Option 1 = "N", Additional Option 2 = "Y" | Charge = RM 13.65 | - | Charge = RM 13.65 | Pass | -
| 2.1.24 |  | Calculate the charge of Normal (4R) photo with quantity of 50, with design effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 1, Quantity = 50, Additional Option 1 = "N", Additional Option 2 = "Y" | Charge = RM 32.5 | - | Charge = RM 32.5 | Pass | -
| 2.1.25 |  | Calculate the charge of Normal (4R) photo with quantity of 1, with high quality paper and design effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 1, Quantity = 1, Additional Option 1 = "Y", Additional Option 2 = "Y" | Charge = RM 1.25 | - | Charge = RM 1.25 | Pass | -
| 2.1.26 |  | Calculate the charge of Normal (4R) photo with quantity of 4, with high quality paper and design effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 1, Quantity = 4, Additional Option 1 = "Y", Additional Option 2 = "Y" | Charge = RM 5 | - | Charge = RM 5 | Pass | -
| 2.1.27 |  | Calculate the charge of Normal (4R) photo with quantity of 5, with high quality paper and design effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 1, Quantity = 5, Additional Option 1 = "Y", Additional Option 2 = "Y" | Charge = RM 5.75 | - | Charge = RM 5.75 | Pass | -
| 2.1.28 |  | Calculate the charge of Normal (4R) photo with quantity of 10, with high quality paper and design effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 1, Quantity = 10, Additional Option 1 = "Y", Additional Option 2 = "Y" | Charge = RM 11.5 | - | Charge = RM 11.5 | Pass | -
| 2.1.29 |  | Calculate the charge of Normal (4R) photo with quantity of 11, with high quality paper and design effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 1, Quantity = 11, Additional Option 1 = "Y", Additional Option 2 = "Y" | Charge = RM 11 | - | Charge = RM 11 | Pass | -
| 2.1.30 |  | Calculate the charge of Normal (4R) photo with quantity of 20, with high quality paper and design effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 1, Quantity = 20, Additional Option 1 = "Y", Additional Option 2 = "Y" | Charge = RM 20 | - | Charge = RM 20 | Pass | -
| 2.1.31 |  | Calculate the charge of Normal (4R) photo with quantity of 21, with high quality paper and design effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 1, Quantity = 21, Additional Option 1 = "Y", Additional Option 2 = "Y" | Charge = RM 15.75 | - | Charge = RM 15.75 | Pass | -
| 2.1.32 |  | Calculate the charge of Normal (4R) photo with quantity of 50, with high quality paper and design effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 1, Quantity = 50, Additional Option 1 = "Y", Additional Option 2 = "Y" | Charge = RM 37.5 | - | Charge = RM 37.5 | Pass | -
| 2.2.1 |  | Calculate the charge of Passport photo with quantity of 1, without any additional effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 2, Quantity = 1, Additional Option 1 = "N", Additional Option 2 = "N" | Charge = RM 1.2 | - | Charge = RM 1.2 | Pass | -
| 2.2.2 |  | Calculate the charge of Passport photo with quantity of 4, without any additional effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 2, Quantity = 4, Additional Option 1 = "N", Additional Option 2 = "N" | Charge = RM 4.8 | - | Charge = RM 4.8 | Pass | -
| 2.2.3 |  | Calculate the charge of Passport photo with quantity of 5, without any additional effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 2, Quantity = 5, Additional Option 1 = "N", Additional Option 2 = "N" | Charge = RM 4.75 | - | Charge = RM 4.75 | Pass | -
| 2.2.4 |  | Calculate the charge of Passport photo with quantity of 10, without any additional effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 2, Quantity = 10, Additional Option 1 = "N", Additional Option 2 = "N" | Charge = RM 9.5 | - | Charge = RM 9.5 | Pass | -
| 2.2.5 |  | Calculate the charge of Passport photo with quantity of 11, without any additional effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 2, Quantity = 11, Additional Option 1 = "N", Additional Option 2 = "N" | Charge = RM 9.35 | - | Charge = RM 9.35 | Pass | -
| 2.2.6 |  | Calculate the charge of Passport photo with quantity of 20, without any additional effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 2, Quantity = 20, Additional Option 1 = "N", Additional Option 2 = "N" | Charge = RM 17 | - | Charge = RM 17 | Pass | -
| 2.2.7 |  | Calculate the charge of Passport photo with quantity of 21, without any additional effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 2, Quantity = 21, Additional Option 1 = "N", Additional Option 2 = "N" | Charge = RM 15.75 | - | Charge = RM 15.75 | Pass | -
| 2.2.8 |  | Calculate the charge of Passport photo with quantity of 50, without any additional effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 2, Quantity = 50, Additional Option 1 = "N", Additional Option 2 = "N" | Charge = RM 37.5 | - | Charge = RM 37.5 | Pass | -
| 2.2.9 |  | Calculate the charge of Passport photo with quantity of 1, with high quality paper effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 2, Quantity = 1, Additional Option 1 = "Y", Additional Option 2 = "N" | Charge = RM 1.3 | - | Charge = RM 1.3 | Pass | -
| 2.2.10 |  | Calculate the charge of Passport photo with quantity of 4, with high quality paper effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 2, Quantity = 4, Additional Option 1 = "Y", Additional Option 2 = "N" | Charge = RM 5.2 | - | Charge = RM 5.2 | Pass | -
| 2.2.11 |  | Calculate the charge of Passport photo with quantity of 5, with high quality paper effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 2, Quantity = 5, Additional Option 1 = "Y", Additional Option 2 = "N" | Charge = RM 5.25 | - | Charge = RM 5.25 | Pass | -
| 2.2.12 |  | Calculate the charge of Passport photo with quantity of 10, with high quality paper effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 2, Quantity = 10, Additional Option 1 = "Y", Additional Option 2 = "N" | Charge = RM 10.5 | - | Charge = RM 10.5 | Pass | -
| 2.2.13 |  | Calculate the charge of Passport photo with quantity of 11, with high quality paper effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 2, Quantity = 11, Additional Option 1 = "Y", Additional Option 2 = "N" | Charge = RM 10.45 | - | Charge = RM 10.45 | Pass | -
| 2.2.14 |  | Calculate the charge of Passport photo with quantity of 20, with high quality paper effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 2, Quantity = 20, Additional Option 1 = "Y", Additional Option 2 = "N" | Charge = RM 19 | - | Charge = RM 19 | Pass | -
| 2.2.15 |  | Calculate the charge of Passport photo with quantity of 21, with high quality paper effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 2, Quantity = 21, Additional Option 1 = "Y", Additional Option 2 = "N" | Charge = RM 17.85 | - | Charge = RM 17.85 | Pass | -
| 2.2.16 |  | Calculate the charge of Passport photo with quantity of 50, with high quality paper effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 2, Quantity = 50, Additional Option 1 = "Y", Additional Option 2 = "N" | Charge = RM 42.5 | - | Charge = RM 42.5 | Pass | -
| 2.2.17 |  | Calculate the charge of Passport photo with quantity of 1, with design effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 2, Quantity = 1, Additional Option 1 = "N", Additional Option 2 = "Y" | Charge = RM 1.35 | - | Charge = RM 1.35 | Pass | -
| 2.2.18 |  | Calculate the charge of Passport photo with quantity of 4, with design effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 2, Quantity = 4, Additional Option 1 = "N", Additional Option 2 = "Y" | Charge = RM 5.4 | - | Charge = RM 5.4 | Pass | -
| 2.2.19 |  | Calculate the charge of Passport photo with quantity of 5, with design effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 2, Quantity = 5, Additional Option 1 = "N", Additional Option 2 = "Y" | Charge = RM 5.5 | - | Charge = RM 5.5 | Pass | -
| 2.2.20 |  | Calculate the charge of Passport photo with quantity of 10, with design effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 2, Quantity = 10, Additional Option 1 = "N", Additional Option 2 = "Y" | Charge = RM 11 | - | Charge = RM 11 | Pass | -
| 2.2.21 |  | Calculate the charge of Passport photo with quantity of 11, with design effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 2, Quantity = 11, Additional Option 1 = "N", Additional Option 2 = "Y" | Charge = RM 11 | - | Charge = RM 11 | Pass | -
| 2.2.22 |  | Calculate the charge of Passport photo with quantity of 20, with design effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 2, Quantity = 20, Additional Option 1 = "N", Additional Option 2 = "Y" | Charge = RM 20 | - | Charge = RM 20 | Pass | -
| 2.2.23 |  | Calculate the charge of Passport photo with quantity of 21, with design effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 2, Quantity = 21, Additional Option 1 = "N", Additional Option 2 = "Y" | Charge = RM 18.9 | - | Charge = RM 18.9 | Pass | -
| 2.2.24 |  | Calculate the charge of Passport photo with quantity of 50, with design effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 2, Quantity = 50, Additional Option 1 = "N", Additional Option 2 = "Y" | Charge = RM 45 | - | Charge = RM 45 | Pass | -
| 2.2.25 |  | Calculate the charge of Passport photo with quantity of 1, with high quality paper and design effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 2, Quantity = 1, Additional Option 1 = "Y", Additional Option 2 = "Y" | Charge = RM 1.45 | - | Charge = RM 1.45 | Pass | -
| 2.2.26 |  | Calculate the charge of Passport photo with quantity of 4, with high quality paper and design effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 2, Quantity = 4, Additional Option 1 = "Y", Additional Option 2 = "Y" | Charge = RM 5.8 | - | Charge = RM 5.8 | Pass | -
| 2.2.27 |  | Calculate the charge of Passport photo with quantity of 5, with high quality paper and design effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 2, Quantity = 5, Additional Option 1 = "Y", Additional Option 2 = "Y" | Charge = RM 6 | - | Charge = RM 6 | Pass | -
| 2.2.28 |  | Calculate the charge of Passport photo with quantity of 10, with high quality paper and design effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 2, Quantity = 10, Additional Option 1 = "Y", Additional Option 2 = "Y" | Charge = RM 12 | - | Charge = RM 12 | Pass | -
| 2.2.29 |  | Calculate the charge of Passport photo with quantity of 11, with high quality paper and design effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 2, Quantity = 11, Additional Option 1 = "Y", Additional Option 2 = "Y" | Charge = RM 12.1 | - | Charge = RM 12.1 | Pass | -
| 2.2.30 |  | Calculate the charge of Passport photo with quantity of 20, with high quality paper and design effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 2, Quantity = 20, Additional Option 1 = "Y", Additional Option 2 = "Y" | Charge = RM 22 | - | Charge = RM 22 | Pass | -
| 2.2.31 |  | Calculate the charge of Passport photo with quantity of 21, with high quality paper and design effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 2, Quantity = 21, Additional Option 1 = "Y", Additional Option 2 = "Y" | Charge = RM 21 | - | Charge = RM 21 | Pass | -
| 2.2.32 |  | Calculate the charge of Passport photo with quantity of 50, with high quality paper and design effect | 1. Order has been made and added to the order list. | 1. Calculate Photo Charge | Type = "P", Option = 2, Quantity = 50, Additional Option 1 = "Y", Additional Option 2 = "Y" | Charge = RM 50 | - | Charge = RM 50 | Pass | -
GetTotalChargeValidValues.java | 3.1.1 | Verify the calculation of different types of document/photo with multiple orders | Calculate the charge of 3 Black & White document and 18 Colour document | 1. Orders have been made and added to the order list. 2. Stub is ready for use. | 1. Calculate Total Charge | 1st Order: Type = "D", Option = 1, Quantity = 3, Additional Option 1 = "N", Additional Option 2 = "N" 2nd Order: Type = "D", Option = 2, Quantity = 18, Additional Option 1 = "N", Additional Option 2 = "N" | Charge = RM 15.9 | - | Charge = RM 15.9 | Pass | -
| 3.1.2 |  | Calculate the charge of 7 Black & White document and 6 Normal (4R) photo with high quality paper effect | 1. Orders have been made and added to the order list. 2. Stub is ready for use. | 1. Calculate Total Charge | 1st Order: Type = "D", Option = 1, Quantity = 7, Additional Option 1 = "N", Additional Option 2 = "N" 2nd Order: Type = "P", Option = 1, Quantity = 6, Additional Option 1 = "Y", Additional Option 2 = "N" | Charge = RM 8.8 | - | Charge = RM 8.8 | Pass | -
| 3.1.3 |  | Calculate the charge of 12 Black & White document and 3 Passport photo without any effect | 1. Orders have been made and added to the order list. 2. Stub is ready for use. | 1. Calculate Total Charge | 1st Order: Type = "D", Option = 1, Quantity = 12, Additional Option 1 = "N", Additional Option 2 = "N" 2nd Order: Type = "P", Option = 2, Quantity = 3, Additional Option 1 = "N", Additional Option 2 = "N" | Charge = RM 7.2 | - | Charge = RM 7.2 | Pass | -
| 3.1.4 |  | Calculate the charge of 30 Colour document and 15 Normal (4R) photo with high design paper effect and design effect | 1. Orders have been made and added to the order list. 2. Stub is ready for use. | 1. Calculate Total Charge | 1st Order: Type = "D", Option = 2, Quantity = 30, Additional Option 1 = "N", Additional Option 2 = "N" 2nd Order: Type = "P", Option = 1, Quantity = 15, Additional Option 1 = "Y", Additional Option 2 = "Y" | Charge = RM 36 | - | Charge = RM 36 | Pass | -
| 3.1.5 |  | Calculate the charge of 4 Colour document and 30 Passport document with design effect | 1. Orders have been made and added to the order list. 2. Stub is ready for use. | 1. Calculate Total Charge | 1st Order: Type = "D", Option = 2, Quantity = 4, Additional Option 1 = "N", Additional Option 2 = "N" 2nd Order: Type = "P", Option = 2, Quantity = 30, Additional Option 1 = "N", Additional Option 2 = "Y" | Charge = RM 31 | - | Charge = RM 31 | Pass | -
| 3.1.6 |  | Calculate the charge of 40 Normal (4R) photo without any effect and 17 Passport photo with high design paper effect and design effect | 1. Orders have been made and added to the order list. 2. Stub is ready for use. | 1. Calculate Total Charge | 1st Order: Type = "P", Option = 1, Quantity = 40, Additional Option 1 = "N", Additional Option 2 = "N" 2nd Order: Type = "P", Option = 2, Quantity = 17, Additional Option 1 = "Y", Additional Option 2 = "Y" | Charge = RM 38.7 | - | Charge = RM 38.7 | Pass | -
| 3.1.7 |  | Calculate the charge of 38 Black & White document, 8 Colour document, 3 Normal (4R) photo with design effect | 1. Orders have been made and added to the order list. 2. Stub is ready for use. | 1. Calculate Total Charge | 1st Order: Type = "D", Option = 1, Quantity = 38, Additional Option 1 = "N", Additional Option 2 = "N" 2nd Order: Type = "D", Option = 2, Quantity = 8, Additional Option 1 = "N", Additional Option 2 = "N" 3rd Order: Type = "P", Option = 1, Quantity = 3, Additional Option 1 = "N", Additional Option2 = "Y" | Charge = RM 18.25 | - | Charge = RM 18.25 | Pass | -
| 3.1.8 |  | Calculate the charge of 23 Black & White document, 3 Colour document, and 9 Passport photo with high design paper effect | 1. Orders have been made and added to the order list. 2. Stub is ready for use. | 1. Calculate Total Charge | 1st Order: Type = "D", Option = 1, Quantity = 23, Additional Option 1 = "N", Additional Option 2 = "N" 2nd Order: Type = "D", Option = 2, Quantity = 3, Additional Option 1 = "N", Additional Option 2 = "N" 3rd Order: Type = "P", Option = 2, Quantity = 9, Additional Option 1 = "Y", Additional Option2 = "N" | Charge = RM 17.05 | - | Charge = RM 17.05 | Pass | -
| 3.1.9 |  | Calculate the charge of 14 Black & White document, 9 Normal (4R) photo with design effect, and 13 Passport photo without any effect | 1. Orders have been made and added to the order list. 2. Stub is ready for use. | 1. Calculate Total Charge | 1st Order: Type = "D", Option = 1, Quantity = 14, Additional Option 1 = "N", Additional Option 2 = "N" 2nd Order: Type = "P", Option = 1, Quantity = 9, Additional Option 1 = "N", Additional Option 2 = "Y" 3rd Order: Type = "P", Option = 2, Quantity = 13, Additional Option 1 = "N", Additional Option2 = "N" | Charge = RM 24.7 | - | Charge = RM 24.7 | Pass | -
| 3.1.10 |  | Calculate the charge of 12 Colour document, 18 Normal (4R) photo with high design paper effect, and 3 Passport photo with design effect | 1. Orders have been made and added to the order list. 2. Stub is ready for use. | 1. Calculate Total Charge | 1st Order: Type = "D", Option = 2, Quantity = 12, Additional Option 1 = "N", Additional Option 2 = "N" 2nd Order: Type = "P", Option = 1, Quantity = 18, Additional Option 1 = "Y", Additional Option 2 = "N" 3rd Order: Type = "P", Option = 2, Quantity = 3, Additional Option 1 = "N", Additional Option2 = "Y" | Charge = RM 28.95 | - | Charge = RM 28.95 | Pass | -
| 3.1.11 |  | Calculate the charge of 50 Black & White document, 50 Colour document, 50 Normal (4R) photo with high design paper effect and design effect, and 50 Passport photo with high design paper effect and design effect | 1. Orders have been made and added to the order list. 2. Stub is ready for use. | 1. Calculate Total Charge | 1st Order: Type = "D", Option = 1, Quantity = 50, Additional Option 1 = "N", Additional Option 2 = "N" 2nd Order: Type = "D", Option = 2, Quantity = 50, Additional Option 1 = "N", Additional Option 2 = "N" 3rd Order: Type = "P", Option = 1, Quantity = 50, Additional Option 1 = "Y", Additional Option2 = "Y" 4th Order: Type = "P", Option = 2, Quantity = 50, Additional Option = "Y", Additional Option = "Y" | Charge = RM 132.5 | - | Charge = RM 132.5 | Pass | -
PassPrintingRequestsUnitTests.java | 4.1.1 | Verify the information passed from Charge module to Printing module is correct | If two orders with same type, option, additional option 1, and additional option 2 have been made, then the number of printing request passed is 1, and the quantity of the printing request is the addition quantity from order 1 and order 2 | 1. Orders have been made and added to the order list. 2. Total charges for the order have already been counted. 3. Stub and mock is ready for use. | 1. Pass Printing Requests 2. Get Printing Requests 3. Get Print List | 1st Order: Type = "D", Option = 1, Quantity = 2, Additional Option 1 = "N", Additional Option 2 = "N" 2nd Order: Type = "D", Option = 1, Quantity = 3, Additional Option 1 = "N", Additional Option 2 = "N" | 1st Printing Request: Type = "D", Option = 1, Quantity = 5, Additional Option 1 = "N", Additional Option 2 = "N" | - | 1st Printing Request: Type = "D", Option = 1, Quantity = 5, Additional Option 1 = "N", Additional Option 2 = "N" | Pass | -
| 4.1.2 |  | If two orders with different types/options/additional option 1/ additional option 2 have been made, then the number of printing request passed is 2 | 1. Orders have been made and added to the order list. 2. Total charges for the order have already been counted. 3. Stub and mock is ready for use. | 1. Pass Printing Requests 2. Get Printing Requests 3. Get Print List | 1st Order: Type = "D", Option = 1, Quantity = 2, Additional Option 1 = "N", Additional Option 2 = "N" 2nd Order: Type = "P", Option = 1, Quantity = 2, Additional Option 1 = "N", Additional Option 2 = "N" | 1st Printing Request: Type = "D", Option = 1, Quantity = 2, Additional Option 1 = "N", Additional Option 2 = "N" 2nd Printing Request: Type = "P", Option = 1, Quantity = 2, Additional Option 1 = "N", Additional Option 2 = "N" | - | 1st Printing Request: Type = "D", Option = 1, Quantity = 2, Additional Option 1 = "N", Additional Option 2 = "N" 2nd Printing Request: Type = "P", Option = 1, Quantity = 2, Additional Option 1 = "N", Additional Option 2 = "N" | Pass | -
| 4.1.3 |  | If three orders have been made, and two orders have same type, option, additional option1, and additional option 2, then the number of printing request list is 2 | 1. Orders have been made and added to the order list. 2. Total charges for the order have already been counted. 3. Stub and mock is ready for use. | 1. Pass Printing Requests 2. Get Printing Requests 3. Get Print List | 1st Order: Type = "D", Option = 1, Quantity = 2, Additional Option 1 = "N", Additional Option 2 = "N" 2nd Order: Type = "D", Option = 1, Quantity = 3, Additional Option 1 = "N", Additional Option 2 = "N" 3rd Order: Type = "D", Option = 2, Quantity = 10, Additional Option 1 = "N", Additional Option 2 = "N" | 1st Printing Request: Type = "D", Option = 2, Quantity = 10, Additional Option 1 = "N", Additional Option 2 = "N" 2nd Printing Request: Type = "D", Option = 1, Quantity = 5, Additional Option 1 = "N", Additional Option 2 = "N" | - | 1st Printing Request: Type = "D", Option = 2, Quantity = 10, Additional Option 1 = "N", Additional Option 2 = "N" 2nd Printing Request: Type = "D", Option = 1, Quantity = 5, Additional Option 1 = "N", Additional Option 2 = "N" | Pass | -
| 4.1.4 |  | If four orders have been made, and two orders have same type, option, additional option1, and additional option 2, another two orders also have same type, option, additional option1, and additional option 2. then the number of printing request list is 2 | 1. Orders have been made and added to the order list. 2. Total charges for the order have already been counted. 3. Stub and mock is ready for use. | 1. Pass Printing Requests 2. Get Printing Requests 3. Get Print List | 1st Order: Type = "D", Option = 1, Quantity = 2, Additional Option 1 = "N", Additional Option 2 = "N" 2nd Order: Type = "P", Option = 2, Quantity = 3, Additional Option 1 = "Y", Additional Option 2 = "Y" 3rd Order: Type = "P", Option = 2, Quantity = 5, Additional Option 1 = "Y", Additional Option 2 = "Y" 4th Order: Type = "D", Option = 1, Quantity = 3, Additional Option 1 = "N", Additional Option 2 = "N" | 1st Printing Request: Type = "D", Option = 1, Quantity = 5, Additional Option 1 = "N", Additional Option 2 = "N" 2nd Printing Request: Type = "P", Option = 2, Quantity = 8, Additional Option 1 = "Y", Additional Option 2 = "Y" | - | 1st Printing Request: Type = "D", Option = 1, Quantity = 5, Additional Option 1 = "N", Additional Option 2 = "N" 2nd Printing Request: Type = "P", Option = 2, Quantity = 8, Additional Option 1 = "Y", Additional Option 2 = "Y" | Pass | -
| 4.1.5 |  | If four orders have been made, and three orders have same type, option, additional option1, and additional option 2, then the number of printing request list is 2 | 1. Orders have been made and added to the order list. 2. Total charges for the order have already been counted. 3. Stub and mock is ready for use. | 1. Pass Printing Requests 2. Get Printing Requests 3. Get Print List | 1st Order: Type = "D", Option = 1, Quantity = 3, Additional Option 1 = "N", Additional Option 2 = "N" 2nd Order: Type = "D", Option = 1, Quantity = 9, Additional Option 1 = "N", Additional Option 2 = "N" 3rd Order: Type = "P", Option = 1, Quantity = 3, Additional Option 1 = "Y", Additional Option 2 = "N" 4th Order: Type = "D", Option = 1, Quantity = 12, Additional Option 1 = "N", Additional Option 2 = "N" | 1st Printing Request: Type = "P", Option = 1, Quantity = 3, Additional Option 1 = "Y", Additional Option 2 = "N" 2nd Printing Request: Type = "D", Option = 1, Quantity = 24, Additional Option 1 = "N", Additional Option 2 = "N" | - | 1st Printing Request: Type = "P", Option = 1, Quantity = 3, Additional Option 1 = "Y", Additional Option 2 = "N" 2nd Printing Request: Type = "D", Option = 1, Quantity = 24, Additional Option 1 = "N", Additional Option 2 = "N" | Pass | -
ChargeModuleIntegrationTest.java | 5.1.1 | Verify the calculation of different types of document/photo with multiple orders | Calculate the charge of 3 Black & White document and 18 Colour document | 1. Orders have been made and added to the order list. 2. Stub is ready for use. | 1. Calculate Total Charge | 1st Order: Type = "D", Option = 1, Quantity = 3, Additional Option 1 = "N", Additional Option 2 = "N" 2nd Order: Type = "D", Option = 2, Quantity = 18, Additional Option 1 = "N", Additional Option 2 = "N" | Charge = RM 15.9 | - | Charge = RM 15.9 | Pass | -
| 5.1.2 |  | Calculate the charge of 7 Black & White document and 6 Normal (4R) photo with high quality paper effect | 1. Orders have been made and added to the order list. 2. Stub is ready for use. | 1. Calculate Total Charge | 1st Order: Type = "D", Option = 1, Quantity = 7, Additional Option 1 = "N", Additional Option 2 = "N" 2nd Order: Type = "P", Option = 1, Quantity = 6, Additional Option 1 = "Y", Additional Option 2 = "N" | Charge = RM 8.8 | - | Charge = RM 8.8 | Pass | -
| 5.1.3 |  | Calculate the charge of 12 Black & White document and 3 Passport photo without any effect | 1. Orders have been made and added to the order list. 2. Stub is ready for use. | 1. Calculate Total Charge | 1st Order: Type = "D", Option = 1, Quantity = 12, Additional Option 1 = "N", Additional Option 2 = "N" 2nd Order: Type = "P", Option = 2, Quantity = 3, Additional Option 1 = "N", Additional Option 2 = "N" | Charge = RM 7.2 | - | Charge = RM 7.2 | Pass | -
| 5.1.4 |  | Calculate the charge of 30 Colour document and 15 Normal (4R) photo with high design paper effect and design effect | 1. Orders have been made and added to the order list. 2. Stub is ready for use. | 1. Calculate Total Charge | 1st Order: Type = "D", Option = 2, Quantity = 30, Additional Option 1 = "N", Additional Option 2 = "N" 2nd Order: Type = "P", Option = 1, Quantity = 15, Additional Option 1 = "Y", Additional Option 2 = "Y" | Charge = RM 36 | - | Charge = RM 36 | Pass | -
| 5.1.5 |  | Calculate the charge of 4 Colour document and 30 Passport document with design effect | 1. Orders have been made and added to the order list. 2. Stub is ready for use. | 1. Calculate Total Charge | 1st Order: Type = "D", Option = 2, Quantity = 4, Additional Option 1 = "N", Additional Option 2 = "N" 2nd Order: Type = "P", Option = 2, Quantity = 30, Additional Option 1 = "N", Additional Option 2 = "Y" | Charge = RM 31 | - | Charge = RM 31 | Pass | -
| 5.1.6 |  | Calculate the charge of 40 Normal (4R) photo without any effect and 17 Passport photo with high design paper effect and design effect | 1. Orders have been made and added to the order list. 2. Stub is ready for use. | 1. Calculate Total Charge | 1st Order: Type = "P", Option = 1, Quantity = 40, Additional Option 1 = "N", Additional Option 2 = "N" 2nd Order: Type = "P", Option = 2, Quantity = 17, Additional Option 1 = "Y", Additional Option 2 = "Y" | Charge = RM 38.7 | - | Charge = RM 38.7 | Pass | -
| 5.1.7 |  | Calculate the charge of 38 Black & White document, 8 Colour document, 3 Normal (4R) photo with design effect | 1. Orders have been made and added to the order list. 2. Stub is ready for use. | 1. Calculate Total Charge | 1st Order: Type = "D", Option = 1, Quantity = 38, Additional Option 1 = "N", Additional Option 2 = "N" 2nd Order: Type = "D", Option = 2, Quantity = 8, Additional Option 1 = "N", Additional Option 2 = "N" 3rd Order: Type = "P", Option = 1, Quantity = 3, Additional Option 1 = "N", Additional Option2 = "Y" | Charge = RM 18.25 | - | Charge = RM 18.25 | Pass | -
| 5.1.8 |  | Calculate the charge of 23 Black & White document, 3 Colour document, and 9 Passport photo with high design paper effect | 1. Orders have been made and added to the order list. 2. Stub is ready for use. | 1. Calculate Total Charge | 1st Order: Type = "D", Option = 1, Quantity = 23, Additional Option 1 = "N", Additional Option 2 = "N" 2nd Order: Type = "D", Option = 2, Quantity = 3, Additional Option 1 = "N", Additional Option 2 = "N" 3rd Order: Type = "P", Option = 2, Quantity = 9, Additional Option 1 = "Y", Additional Option2 = "N" | Charge = RM 17.05 | - | Charge = RM 17.05 | Pass | -
| 5.1.9 |  | Calculate the charge of 14 Black & White document, 9 Normal (4R) photo with design effect, and 13 Passport photo without any effect | 1. Orders have been made and added to the order list. 2. Stub is ready for use. | 1. Calculate Total Charge | 1st Order: Type = "D", Option = 1, Quantity = 14, Additional Option 1 = "N", Additional Option 2 = "N" 2nd Order: Type = "P", Option = 1, Quantity = 9, Additional Option 1 = "N", Additional Option 2 = "Y" 3rd Order: Type = "P", Option = 2, Quantity = 13, Additional Option 1 = "N", Additional Option2 = "N" | Charge = RM 24.7 | - | Charge = RM 24.7 | Pass | -
| 5.1.10 |  | Calculate the charge of 12 Colour document, 18 Normal (4R) photo with high design paper effect, and 3 Passport photo with design effect | 1. Orders have been made and added to the order list. 2. Stub is ready for use. | 1. Calculate Total Charge | 1st Order: Type = "D", Option = 2, Quantity = 12, Additional Option 1 = "N", Additional Option 2 = "N" 2nd Order: Type = "P", Option = 1, Quantity = 18, Additional Option 1 = "Y", Additional Option 2 = "N" 3rd Order: Type = "P", Option = 2, Quantity = 3, Additional Option 1 = "N", Additional Option2 = "Y" | Charge = RM 28.95 | - | Charge = RM 28.95 | Pass | -
| 5.1.11 |  | Calculate the charge of 50 Black & White document, 50 Colour document, 50 Normal (4R) photo with high design paper effect and design effect, and 50 Passport photo with high design paper effect and design effect | 1. Orders have been made and added to the order list. 2. Stub is ready for use. | 1. Calculate Total Charge | 1st Order: Type = "D", Option = 1, Quantity = 50, Additional Option 1 = "N", Additional Option 2 = "N" 2nd Order: Type = "D", Option = 2, Quantity = 50, Additional Option 1 = "N", Additional Option 2 = "N" 3rd Order: Type = "P", Option = 1, Quantity = 50, Additional Option 1 = "Y", Additional Option2 = "Y" 4th Order: Type = "P", Option = 2, Quantity = 50, Additional Option = "Y", Additional Option = "Y" | Charge = RM 132.5 | - | Charge = RM 132.5 | Pass | -
| 5.2.1 | Verify the information passed from Charge module to Printing module is correct | If two orders with same type, option, additional option 1, and additional option 2 have been made, then the number of printing request passed is 1, and the quantity of the printing request is the addition quantity from order 1 and order 2 | 1. Orders have been made and added to the order list. 2. Total charges for the order have already been counted. 3. Stub and mock is ready for use. | 1. Pass Printing Requests 2. Get Printing Requests 3. Get Print List | 1st Order: Type = "D", Option = 1, Quantity = 2, Additional Option 1 = "N", Additional Option 2 = "N" 2nd Order: Type = "D", Option = 1, Quantity = 3, Additional Option 1 = "N", Additional Option 2 = "N" | 1st Printing Request: Type = "D", Option = 1, Quantity = 5, Additional Option 1 = "N", Additional Option 2 = "N" | - | 1st Printing Request: Type = "D", Option = 1, Quantity = 5, Additional Option 1 = "N", Additional Option 2 = "N" | Pass | -
| 5.2.2 |  | If two orders with different types/options/additional option 1/ additional option 2 have been made, then the number of printing request passed is 2 | 1. Orders have been made and added to the order list. 2. Total charges for the order have already been counted. 3. Stub and mock is ready for use. | 1. Pass Printing Requests 2. Get Printing Requests 3. Get Print List | 1st Order: Type = "D", Option = 1, Quantity = 2, Additional Option 1 = "N", Additional Option 2 = "N" 2nd Order: Type = "P", Option = 1, Quantity = 2, Additional Option 1 = "N", Additional Option 2 = "N" | 1st Printing Request: Type = "D", Option = 1, Quantity = 2, Additional Option 1 = "N", Additional Option 2 = "N" 2nd Printing Request: Type = "P", Option = 1, Quantity = 2, Additional Option 1 = "N", Additional Option 2 = "N" | - | 1st Printing Request: Type = "D", Option = 1, Quantity = 2, Additional Option 1 = "N", Additional Option 2 = "N" 2nd Printing Request: Type = "P", Option = 1, Quantity = 2, Additional Option 1 = "N", Additional Option 2 = "N" | Pass | -
| 5.2.3 |  | If three orders have been made, and two orders have same type, option, additional option1, and additional option 2, then the number of printing request list is 2 | 1. Orders have been made and added to the order list. 2. Total charges for the order have already been counted. 3. Stub and mock is ready for use. | 1. Pass Printing Requests 2. Get Printing Requests 3. Get Print List | 1st Order: Type = "D", Option = 1, Quantity = 2, Additional Option 1 = "N", Additional Option 2 = "N" 2nd Order: Type = "D", Option = 1, Quantity = 3, Additional Option 1 = "N", Additional Option 2 = "N" 3rd Order: Type = "D", Option = 2, Quantity = 10, Additional Option 1 = "N", Additional Option 2 = "N" | 1st Printing Request: Type = "D", Option = 2, Quantity = 10, Additional Option 1 = "N", Additional Option 2 = "N" 2nd Printing Request: Type = "D", Option = 1, Quantity = 5, Additional Option 1 = "N", Additional Option 2 = "N" | - | 1st Printing Request: Type = "D", Option = 2, Quantity = 10, Additional Option 1 = "N", Additional Option 2 = "N" 2nd Printing Request: Type = "D", Option = 1, Quantity = 5, Additional Option 1 = "N", Additional Option 2 = "N" | Pass | -
| 5.2.4 |  | If four orders have been made, and two orders have same type, option, additional option1, and additional option 2, another two orders also have same type, option, additional option1, and additional option 2. then the number of printing request list is 2 | 1. Orders have been made and added to the order list. 2. Total charges for the order have already been counted. 3. Stub and mock is ready for use. | 1. Pass Printing Requests 2. Get Printing Requests 3. Get Print List | 1st Order: Type = "D", Option = 1, Quantity = 2, Additional Option 1 = "N", Additional Option 2 = "N" 2nd Order: Type = "P", Option = 2, Quantity = 3, Additional Option 1 = "Y", Additional Option 2 = "Y" 3rd Order: Type = "P", Option = 2, Quantity = 5, Additional Option 1 = "Y", Additional Option 2 = "Y" 4th Order: Type = "D", Option = 1, Quantity = 3, Additional Option 1 = "N", Additional Option 2 = "N" | 1st Printing Request: Type = "D", Option = 1, Quantity = 5, Additional Option 1 = "N", Additional Option 2 = "N" 2nd Printing Request: Type = "P", Option = 2, Quantity = 8, Additional Option 1 = "Y", Additional Option 2 = "Y" | - | 1st Printing Request: Type = "D", Option = 1, Quantity = 5, Additional Option 1 = "N", Additional Option 2 = "N" 2nd Printing Request: Type = "P", Option = 2, Quantity = 8, Additional Option 1 = "Y", Additional Option 2 = "Y" | Pass | -
| 5.2.5 |  | If four orders have been made, and three orders have same type, option, additional option1, and additional option 2, then the number of printing request list is 2 | 1. Orders have been made and added to the order list. 2. Total charges for the order have already been counted. 3. Stub and mock is ready for use. | 1. Pass Printing Requests 2. Get Printing Requests 3. Get Print List | 1st Order: Type = "D", Option = 1, Quantity = 3, Additional Option 1 = "N", Additional Option 2 = "N" 2nd Order: Type = "D", Option = 1, Quantity = 9, Additional Option 1 = "N", Additional Option 2 = "N" 3rd Order: Type = "P", Option = 1, Quantity = 3, Additional Option 1 = "Y", Additional Option 2 = "N" 4th Order: Type = "D", Option = 1, Quantity = 12, Additional Option 1 = "N", Additional Option 2 = "N" | 1st Printing Request: Type = "P", Option = 1, Quantity = 3, Additional Option 1 = "Y", Additional Option 2 = "N" 2nd Printing Request: Type = "D", Option = 1, Quantity = 24, Additional Option 1 = "N", Additional Option 2 = "N" | - | 1st Printing Request: Type = "P", Option = 1, Quantity = 3, Additional Option 1 = "Y", Additional Option 2 = "N" 2nd Printing Request: Type = "D", Option = 1, Quantity = 24, Additional Option 1 = "N", Additional Option 2 = "N" | Pass | -

## Printing Module
Project Name: | Printing Kiosk System | Test Designed by: | Yoon Wei Kai
Module Name: | Printing Module | Test Designed date: | 2023-04-14
Release Version: | V 1.3 | Test Executed by: | E Zhong Lin
|  | Test Execution date: | 2023-04-18
Pre-condition | -
Dependencies: | -
Test Priority | 3 (High)
Test File Name | Test Case# | Test Title | Test Summary | Pre-condition | Test Steps | Test Data | Expected Result | Post-condition | Actual Result | Status | Notes
PrintingUnitTests.java | 1.1.1 | Verify Printing Request that is received from the Charge module is correct | Pass valid printingList | 1. Order has been made. 2. Total charge of the order has been calculated. 3. Printing List is initialized. 4. Charge module has passed the information to Printing module. | 1. Queue Request 2. Get Printing List | Type = "D" Option = 1 Quantity = 1 Additional Option 1 = "N" Additional Option 2 = "N" | new Order[] {"D", 1, 2, "N", "N"} | - | new Order[] {"D", 1, 2, "N", "N"} | Pass | -